## Size Estimating Template
/Proyectos/PSP2 Calculos Regresion
Size Estimating Template (instructions...)
The PROBE Wizard uses Estimated Proxy Size as the basis for generating final estimates for size and time. However, after you last ran the PROBE Wizard, you modified the estimates on this form, causing the Estimated Proxy Size to change. Your current PROBE estimates are based upon the old value of Estimated Proxy Size. To resolve this problem, you should double-check the values in the form below, then run the PROBE Wizard again.
Project Owner | Johann De Jesus Olaya Herrera
Size Measure | LOC
BASE PARTS |  |  | Estimated |  |  |  |  | Actual
|  |  | BASE | DELETED | MODIFIED | ADDED |  | BASE | DELETED | MODIFIED | ADDED
NumeroNodo |  |  | 14 | 0 | 2 | 6 |  | 14 | 0 | 11 | 6
EstadisticoControlador |  |  | 50 | 20 | 2 | 8 |  | 50 | 15 | 4 | 12
EstadisticoModelo |  |  | 33 | 9 | 5 | 85 |  | 33 | 8 | 8 | 83
EstadisticoVista |  |  | 30 | 3 | 1 | 6 |  | 30 | 3 | 4 | 21
add more rows for base parts... | Total: |  | 127 | 32 | 10 | 105 |  | 127 | 26 | 27 | 122
PARTS ADDITIONS |  |  | Estimated | [5 empty] | Actual
|  |  | TYPE | ITEMS | REL. SIZE | SIZE | NR |  | SIZE | ITEMS | NR
0
add more rows for parts additions... |  |  |  | Total: |  | 0 |  |  | 0
REUSED PARTS |  |  | Estimated |  | Actual
|  |  | SIZE |  | SIZE
|  |  | 0 |  | 0
add more rows for reused parts... | Total: |  | 0 |  | 0
TOTAL SIZE |  | Actual
SIZE
Actual Size of Finished Product: |  | 223
Instructions: During the planning phase, complete the "Estimated" columns in the form above, then use the PROBE Wizard to fill out the fields below.
|  |  | SIZE |  | TIME
Added Size (A): | A = BA + PA |  | 105
Estimated Proxy Size (E): | E = BA + PA + M |  | 115
Last Estimated Proxy Size: (The value used on the last run of the PROBE Wizard) |  |  | 115
PROBE estimating basis used: (A, B, C, or D) |  |  | C2 |  | C2
Correlation: (r2) |  |  | N/A |  | N/A
Regression Parameters: | B0 (size and time) |  | 0 |  | 0
Regression Parameters: | B1 (size and time) |  | 1.28 |  | 2.97
Projected Added and Modified Size (P): | P = B0size + B1size * E |  | 147
Estimated Total Size (T): | T = P + B - D - M + R |  | 232
Estimated Total New Reusable (NR): | (sum of NR items) |  | 0
Estimated Total Development Time: | Time = B0time + B1time * E |  |  |  | 0.23681
Prediction Range: | Range |  | N/A |  | N/A
Upper Prediction Interval: | UPI = P + Range |  | N/A |  | N/A
Lower Prediction Interval: | LPI = P - Range |  | N/A |  | N/A
Prediction Interval Percent: |  |  | N/A |  | N/A
View PROBE Report
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.